## Sheet1
| Typical Completion Time | Wyoming | Washington Office | New Mexico/ Oklahoma/ Texas | Eastern States | Oregon/ Washington | Utah | NTC | Nevada | Montana/ Dakotas | NIFC | Idaho | Alaska | Arizona | Colorado | NOC | California
EMS Development
Presentation to Leadership Team |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-02-15 | 2012-03-15
CFT Selected/EMS Introduction and Training | Start date | Completed | 2012-05-01 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-03-14 | Completed | 2012-02-15 | 2012-02-29 | 2012-03-28
Identification of Aspects | 1 week after CFT training | Completed | 2012-05-08 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-03-21 | Completed | 2012-02-22 | 2012-03-07 | 2012-04-04
EMS Policy IM Issued | 2 weeks after CFT training | Completed | 2012-05-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-03-28 | Completed | 2012-02-29 | 2012-03-14 | 2012-04-11
Identification of Significant Aspects by the CFT | 2 weeks after aspects identified | Completed | 2012-05-29 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-04-04 | Completed | 2012-03-07 | 2012-03-21 | 2012-04-18
Leadership Team Review and Approval of the Significant Aspects, Objectives, and Targets | 4 weeks after significant aspects are identified | Completed | 2012-06-29 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-05-02 | 2012-03-15 | 2012-04-04 | 2012-04-18 | 2012-05-16
Development and Review of EMPs | 4 weeks after Apsects, Objectives, and Targets approval | 2012-05-01 | 2012-07-29 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-02-15 | Completed | 2012-05-30 | 2012-04-15 | 2012-05-02 | 2012-05-16 | 2012-06-13
Finalizing the EMS Implementation Plan | 4 weeks after the EMP approval | Completed | 2012-08-29 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2012-03-15 | Completed | 2012-06-27 | 2012-05-15 | 2012-05-30 | 2012-06-13 | 2012-07-11
Employees Trained and EMS Implementation IM Issued - EMS IMPLEMENTATION HAS BEGUN | 1 week after finalizing the EMS Implementation Plan | 2012-05-01 | 2012-09-05 | Completed | Completed | Completed | 2012-04-01 | Completed | Completed | Completed | 2012-03-22 | Completed | 2012-07-04 | 2012-05-22 | 2012-06-06 | 2012-06-20 | 2012-07-18
Third party audit of EMS performed and will be performed every four years there after | 60 weeks after EMS implementation | 8/1/12 (internal) | 2013-11-05 | 2012-08-29 | 2013-03-12 | Completed | 2013-06-01 | 2012-12-19 | Completed | 2012-07-18 | 2013-05-22 | 2012-12-14 | 2013-08-21 | 2013-07-22 | 2013-07-24 | 2013-08-07 | 2013-09-04
Presentation to senior management on third party audit findings and recommended corrective actions | 64 weeks after EMS implementation | 2012-09-01 | 2013-12-05 | 2012-09-29 | 2013-04-12 | Completed | 2013-07-01 | 2013-02-16 | Completed | 2012-08-18 | 2013-06-22 | 2013-01-14 | 2013-09-18 | 2013-08-22 | 2013-08-21 | 2013-09-04 | 2013-10-02
Issuance of self-declaration of conformance that the organization has fully implemented its EMS | 65 weeks after EMS implementation | 2012-09-08 | 2013-12-12 | 2012-10-06 | 2013-04-19 | Completed | 2013-07-08 | 2013-02-23 | Completed | 2012-08-25 | 2013-06-29 | 2013-01-21 | 2013-09-25 | 2013-08-28 | 2013-08-28 | 2013-09-11 | 2013-10-09
Note: The only EMS implementation steps shown in this condensed table are related to the mandatory third party audit. All of the initial and continued EMS implementation steps States and Centers are expected to take are outlined in spreadsheet that was emailed to the States and Centers by WO 280. States and Centers are to completed the entire spreadsheet including dates for the initial and continued implementation of their EMS.]