## EMS Overall Process
| Typical Completion Time | Wyoming | Washington Office | New Mexico/ Oklahoma/ Texas | Eastern States | Oregon/ Washington | Utah | NTC | Nevada | Montana/ Dakotas | NIFC | Idaho | Alaska | Arizona | California | Colorado | NOC
EMS Development
Presentation to Leadership Team | 2012-03-31
Selection of Cross Functional Team CFT) | 2 weeks from Leadership Team presentation
EMS Training for CFT | 2 weeks from selection of CFT
Identification of Aspects | 3 weeks after CFT training
EMS Policy IM Issued | 3 weeks after CFT training
Identification of Significant Aspects by the CFT | 2 weeks after aspects identified
Drafting of Objectives and Targets | 4 weeks after significant aspects are identified
Leadership Team Review and Approval of the Significant Aspects, Objectives, and Targets | 3 weeks after the CFT's review of the objectives and targets
Drafting of Environmental Management Programs (EMP) | 4 weeks after management approval of objectives and targets
Management Review and Approval of EMPs | 3 weeks after the CFT's review of the objectives and targets
Drafting and Review of the EMS Implementation Plan and EMS Implementation IM | 4 weeks after management approval of the EMPs
Finalizing the EMS Implementation Plan | 3 weeks after the CFT's approval of the draft plan
EMS Implementation IM Issued - EMS IMPLEMENTATION HAS BEGUN (31 weeks) | 1 week after finalizing the EMS Implementation Plan
EMS Initial Implementation Underway
All employee EMS training | 3 weeks after EMS implementation IM is issued
EMS calendar of meetings and other activities sent to CFT members and other employees assigned EMS roles by EMS Coordinator | 4 weeks after EMS implementation IM is issued
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 12 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 24 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 36 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Agenda for next Leadership Team includes decision on next year's EMS aspects, objectives and targets; and nominations for next year's CFT members including EMS Management Representative and EMS Coordinator | 44 to 48 weeks after EMS implementation began
Internal audit of the organization's EMS done by the EMS Management Representative and EMS Coordinator | 48 to 50 weeks after implementation began
CFT reviews EMS accomplishments, selects significant aspects, and proposes new objectives and targets and/or a continuation of existing objectives and targets for next year's EMS | 48 weeks after EMS implementation began
Presentation of Annual EMS Accomplishments Report to Leadership Team along with proposed aspects, objectives, and targets for next year's EMS | 52 weeks after implementation began
Direction and comments provided by Leadership Team on EMS accomplishments and the CFT proposal for next year's aspects, objectives, and targets | 52 weeks after implementation began
New CFT is formed by Leadership Team including EMS Management Representative and EMS Coordinator | 52 weeks after implementation began
EMS Implementation Continues - Continual Improvement
Initial CFT meeting with EMS roles and responsibilities assigned | 2 weeks after continuation of EMS implementation
EMS calendar of meetings and other activities sent to CFT members and other employees assigned EMS roles by EMS Coordinator | 3 weeks after continuation of EMS implementation
New EMPs prepared and provided to EMS Management Representative and EMS Coordinator | 4 weeks after continuation of EMS implementation
IM on continued EMS implementation issued | 6 weeks after continuation of EMS implementation
Third party audit of EMS performed and will be performed every four years there after | 8 weeks after new CFT is formed
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 12 weeks after EMS implementation began
Presentation to senior management on third party audit findings and recommended corrective actions | 13 weeks after EMS implementation began
Issuance of self-declaration of conformance that the organization has fully implemented its EMS | 15 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 24 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 36 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Get on Leadership Team's fourth quarter agenda for presentation on EMS accomplishments; proposed aspects, objectives, and targets; and forming next year's CFT | 46 to 48 weeks after EMS implementation began
CFT and other employees assigned EMS rolls meet to review accomplishments, review aspects, select significant aspects, and propose new and/or a continuation of existing aspects, objectives and targets | 48 weeks after EMS implementation began
Internal audit of organization's EMS done by EMS Management Representative and EMS Coordinator | 48 weeks after implementation began
EMS accomplishments, proposed aspects, objectives, and targets; and internal audit findings presented to the Leadership Team | 52 weeks after implementation began
Leadership Team reviews EMS accomplishments and CFT proposal for next year and provides direction on aspects, objectives, and targets and how to improve EMS implementation | 52 weeks after implementation began
Direction and comments provided by Leadership Team on the CFT proposal for next year's aspects, objectives, and targets; improvements to the EMS; and the new CFT members | 52 weeks after implementation began
EMS implementation continues starting at line 32

## EMS Development
EMS Development | Typical Completion Time | Wyoming | Washington Office | New Mexico/ Oklahoma/ Texas | Eastern States | Oregon/ Washington | Utah | NTC | Nevada | Montana/ Dakotas | NIFC | Idaho | Alaska | Arizona | California | Colorado | NOC
Presentation to Leadership Team | 2012-03-31
Selection of Cross Functional Team CFT) | 2 weeks from Leadership Team presentation
EMS Training for CFT | 2 weeks from selection of CFT
Identification of Aspects | 3 weeks after CFT training
EMS Policy IM Issued | 3 weeks after CFT training
Identification of Significant Aspects by the CFT | 2 weeks after aspects identified
Drafting of Objectives and Targets | 4 weeks after significant aspects are identified
Leadership Team Review and Approval of the Significant Aspects, Objectives, and Targets | 3 weeks after the CFT's review of the objectives and targets
Drafting of Environmental Management Programs (EMP) | 4 weeks after management approval of objectives and targets
Management Review and Approval of EMPs | 3 weeks after the CFT's review of the objectives and targets
Drafting and Review of the EMS Implementation Plan and EMS Implementation IM | 4 weeks after management approval of the EMPs
Finalizing the EMS Implementation Plan | 3 weeks after the CFT's approval of the draft plan
EMS Implementation IM Issued - EMS IMPLEMENTATION HAS BEGUN (31 weeks) | 1 week after finalizing the EMS Implementation Plan

## EMS Initial Implementation
EMS Initial Implementation Underway | Typical Completion Time | Wyoming | Washington Office | New Mexico/ Oklahoma/ Texas | Eastern States | Oregon/ Washington | Utah | NTC | Nevada | Montana/ Dakotas | NIFC | Idaho | Alaska | Arizona | California | Colorado | NOC
All employee EMS training | 3 weeks after EMS implementation IM is issued
EMS calendar of meetings and other activities sent to CFT members and other employees assigned EMS roles by EMS Coordinator | 4 weeks after EMS implementation IM is issued
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 12 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 24 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 36 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Agenda for next Leadership Team includes decision on next year's EMS aspects, objectives and targets; and nominations for next year's CFT members including EMS Management Representative and EMS Coordinator | 44 to 48 weeks after EMS implementation began
Internal audit of the organization's EMS done by the EMS Management Representative and EMS Coordinator | 48 to 50 weeks after implementation began
CFT reviews EMS accomplishments, selects significant aspects, and proposes new objectives and targets and/or a continuation of existing objectives and targets for next year's EMS | 48 weeks after EMS implementation began
Presentation of Annual EMS Accomplishments Report to Leadership Team along with proposed aspects, objectives, and targets for next year's EMS | 52 weeks after implementation began
Direction and comments provided by Leadership Team on EMS accomplishments and the CFT proposal for next year's aspects, objectives, and targets | 52 weeks after implementation began
New CFT is formed by Leadership Team including EMS Management Representative and EMS Coordinator | 52 weeks after implementation began

## EMS Continued Implementation
EMS Implementation Continues - Continual Improvement | Typical Completion Time | Wyoming | Washington Office | New Mexico/ Oklahoma/ Texas | Eastern States | Oregon/ Washington | Utah | NTC | Nevada | Montana/ Dakotas | NIFC | Idaho | Alaska | Arizona | California | Colorado | NOC
Initial CFT meeting with EMS roles and responsibilities assigned | 2 weeks after continuation of EMS implementation
EMS calendar of meetings and other activities sent to CFT members and other employees assigned EMS roles by EMS Coordinator | 3 weeks after continuation of EMS implementation
New EMPs prepared and provided to EMS Management Representative and EMS Coordinator | 4 weeks after continuation of EMS implementation
IM on continued EMS implementation issued | 6 weeks after continuation of EMS implementation
Third party audit of EMS performed and will be performed every four years there after | 8 weeks after new CFT is formed
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 12 weeks after EMS implementation began
Presentation to senior management on third party audit findings and recommended corrective actions | 13 weeks after EMS implementation began
Issuance of self-declaration of conformance that the organization has fully implemented its EMS | 15 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 24 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Quarterly reporting by CFT and other employees assigned EMS roles to EMS Coordinator & EMS Management Representative on objectives and targets | 36 weeks after EMS implementation began
Updates on EMS activities and accomplishments to the Leadership Team by the EMS Management Representative | Next meeting or conference call after quarterly CFT meeting
Get on Leadership Team's fourth quarter agenda for presentation on EMS accomplishments; proposed aspects, objectives, and targets; and forming next year's CFT | 46 to 48 weeks after EMS implementation began
CFT and other employees assigned EMS rolls meet to review accomplishments, review aspects, select significant aspects, and propose new and/or a continuation of existing aspects, objectives and targets | 48 weeks after EMS implementation began
Internal audit of organization's EMS done by EMS Management Representative and EMS Coordinator | 48 weeks after implementation began
EMS accomplishments, proposed aspects, objectives, and targets; and internal audit findings presented to the Leadership Team | 52 weeks after implementation began
Leadership Team reviews EMS accomplishments and CFT proposal for next year and provides direction on aspects, objectives, and targets and how to improve EMS implementation | 52 weeks after implementation began
Direction and comments provided by Leadership Team on the CFT proposal for next year's aspects, objectives, and targets; improvements to the EMS; and the new CFT members | 52 weeks after implementation began
EMS implementation continues starting at line 2