## ROW Summary
BLM ROW | ROW TYPE | RCE
WYW-65819 | Pipeline | 2608.1966 | Waiting on Bond Submission | 2016-03-22
WYW-142481 | Road | 139418.7556 | Waiting on Bond submission | 2016-03-22
WYW-163391 | Maintain well pad on federal lands | 34478.2305 | Waiting on Bond Submission | 2016-03-22
WYW-170769 | Maintain multi-well pad on federal lands (no underlying oil and gas lease) | 147275.1456 | Bond submitted and accepted assignment approved |  | 2015-10-08
WYW-67639 | Road & Meter | 8011.1497 | Waiting on Bond Submission | 2016-03-22
WYW-143277 | Water Treatment Facility | 10823.128
WYW-170770 | Power Line | 0 | Bond is required waiting on estimate and submission |  |  | 2016-03-22
ASSUMPTIONS:
1 | Volume of material for road work was estimated to be the same as the material removed
from the ditches 1' deep with 3:1 slope - 6 cubic feet per foot of ROW.
2 | There is no salvage value for any materials removed; culverts, tanks, etc.
3 | Topsoil volume = ROW width x ROW length x 6" thick.
4 | The same amount of time is required by the BLM Procurement Specialist to prepare
necessary contract documents, regardless of the project size.
5 | The BLM Engineer will be on-site during most of the construction. Does not include
travel time or travel expenses.
6 | Assumed that pipeline ROWs do not require revegetation.
7 | No costs were developed for power lines. Power lines assumed to belong to utility
company.
8 | Estimates are based on ROW written descriptions and attached maps. No field
verification was performed. This includes the number of culverts.
9 | Erosion control includes snow fence and/or silt fence. The cost of snow fence was used
since it was the most expensive. Actual locations were not determined.
10 | Costs do not include:
Inspection and re-seeding as result of inspection.
Preparation of SWPPP if required and associated inspections.
11 | Cost estimate includes a 10% contingency factor.

## WYW-65819
BLM ROW | WYW-65819
ROW TYPE | Pipeline | 0.138 | Acres | 50' ROW | 120 | Feet
Location | See ROW Agreement
Task | Description | Staff/Item | Quantity | Unit Cost | Rate (1) | Total
Direct Costs
1 | Mob/Demob - Backhoe | Backhoe w/ oper | 1 | Each | 505 | 505
2 | Excavate at each end of line
3 | Vac fluids from line and flush
4 | Backfill and seed
6 | Seeding (broadcast by hand)
| Seed |  | 6.0113 | M.S.F | 65 | 390.7332
| Fertilize |  | 0.138 | Acre | 265 | 36.57
| Mulch |  | 6.0113 | M.S.F | 61.5 | 369.6937
| Subtotal |  |  |  |  | 1301.9969
| Contingency 10% |  |  |  |  | 130.1997
| Subtotal |  |  |  |  | 1432.1966
(1) From: RS Means Heavy Construction Cost Data (2014)
BLM Administration
| Procurement Spec | Procurement Spec | 32 | Hour | 20 | 640
| Engineer | Engineer | 16 | Hour | 33.5 | 536
| Subtotal |  |  |  |  | 1176
| Grand Total |  |  |  |  | 2608.1966

## WYW-142481
BLM ROW | WYW-142481
ROW TYPE | Road | 10 | Acres | 75' ROW | 5800 | Feet
Location | See ROW Agreement
Task | Description | Staff/Item | Quantity | Unit Cost | Rate (1) | Total
Direct Costs
1 | Mob/Demob - Dozer & Excavator | Dozer & Excavator | 2 | Each | 505 | 1010
2 | Recontour to preconstruction contours with dozer | Dozer w/ oper | 1288.8889 | C.Y. | 4.67 | 6019.1111
3 | Remove CMP culverts (2 - 18") (4 hours each) | Excavator w/ oper | 8 | Hour | 270 | 2160
4 | Apply top soil from pile or along edges of ROW |  | 8066.6667 | C.Y. | 6.4 | 51626.6667
5 | Mob/Demob - Seeding equipment |  | 1 | Each | 505 | 505
6 | Seeding
| Seed |  | 435.6 | M.S.F | 65 | 28314
| Fertilize |  | 10 | Acre | 265 | 2650
| Mulch |  | 435.6 | M.S.F | 61.5 | 26789.4
7 | Erosion control | Snow/silt fence | 580 | L.F | 3.82 | 2215.6
| Subtotal |  |  |  |  | 121289.7778
| Contingency 10% |  |  |  |  | 12128.9778
| Subtotal |  |  |  |  | 133418.7556
(1) From: RS Means Heavy Construction Cost Data (2014)
BLM Administration
| Procurement Spec | Procurement Spec | 32 | Hour | 20 | 640
| Engineer | Engineer | 160 | Hour | 33.5 | 5360
| Subtotal |  |  |  |  | 6000
| Grand Total |  |  |  |  | 139418.7556

## WYW-163391
BLM ROW
ROW TYPE | Well Pad | 2.75 | Acres | 330' x 400'
Location | See ROW Agreement | 1616 cy topsoil | 651 cy fill
Task | Description | Staff/Item | Quantity | Unit Cost | Rate (1) | Total
Direct Costs
1 | Mob/Demob - Dozer |  | 1 | Each | 505 | 505
2 | Recontour to preconstruction contours with dozer | Dozer w/ oper | 651 | C.Y. | 4.67 | 3040.17
3 | Remove CMP culvert | Excavator w/ oper | 0 | Hour | 270 | 0
4 | Apply top soil from pile or along edges of ROW |  | 1616 | C.Y. | 6.4 | 10342.4
5 | Mob/Demob - Seeding equipment |  | 1 | Each | 505 | 505
6 | Seeding |  |  |  | 0
| Seed |  | 119.79 | M.S.F | 65 | 7786.35
| Fertilize |  | 2.75 | Acre | 265 | 728.75
| Mulch |  | 119.79 | M.S.F | 61.5 | 7367.085
7 | Erosion control | Snow/silt fence | 0 | L.F | 3.82 | 0
| Subtotal |  |  |  |  | 30274.755
| Contingency 10% |  |  |  |  | 3027.4755
| Subtotal |  |  |  |  | 33302.2305
(1) From: RS Means Heavy Construction Cost Data (2014)
BLM Administration
| Procurement Spec | Procurement Spec | 32 | Hour | 20 | 640
| Engineer | Engineer | 16 | Hour | 33.5 | 536
| Subtotal |  |  |  |  | 1176
| Grand Total |  |  |  |  | 34478.2305

## WYW-170769
BLM ROW | WYW-170769
ROW TYPE | Well Pad | 11.06 | Acres | 330' x 400'
Location | See ROW Agreement | 8921.7 cy topsoil | 651 cy fill
Task | Description | Staff/Item | Quantity | Unit Cost | Rate (1) | Total
Direct Costs
1 | Remove equipment | Vac truck w/ driver | 4 | Hour |  | 0
| 3 - storage tanks | Crane w/ operator | 8 | Hour | 303.35 | 2426.8
| 1 - dehydrator with drip tank | Transport/winch | 8 | Hour | 162.46 | 1299.68
| 1 - separator | Roustabout crew | 12 | Hour | 200 | 2400
Misc piping and stairs
2 | Remove fence around storage tanks |  | 300 | L.F. | 3.23 | 969
3 | Mob/Demob - Dozer |  | 1 | Each | 505 | 505
4 | Spread tank berms |  | 45 | C.Y. | 4.67 | 210.15
5 | Recontour to preconstruction contours with dozer | Dozer | 651 | C.Y. | 4.67 | 3040.17
6 | Apply top soil from pile |  | 8921.73 | C.Y. | 6.4 | 57099.072
7 | Mob/Demob - Seeding equipment |  | 1 | Each | 505 | 505
8 | Seeding
| Seed |  | 481.7736 | M.S.F | 65 | 31315.284
| Fertilize |  | 11.06 | Acre | 265 | 2930.9
| Mulch |  | 481.7736 | M.S.F | 61.5 | 29629.0764
7 | Erosion control
| Subtotal |  |  |  |  | 132330.1324
| Contingency 10% |  |  |  |  | 13233.0132
| Subtotal |  |  |  |  | 145563.1456
(1) From: RS Means Heavy Construction Cost Data (2014)
BLM Administration
| Procurement Spec | Procurement Spec | 32 | Hour | 20 | 640
| Engineer | Engineer | 32 | Hour | 33.5 | 1072
| Subtotal |  |  |  |  | 1712
| Grand Total |  |  |  |  | 147275.1456

## WYW-143277
BLM ROW | WYW-143277
ROW TYPE | Water Treatment Facility on Well Pad | 11.06 | Acres | 330' x 400'
Location | See ROW Agreement | 8921.7 cy topsoil | 651 cy fill
Task | Description | Staff/Item | Quantity | Unit Cost | Rate (1) | Total
Direct Costs
1 | Remove equipment | Vac truck w/ driver | 4 | Hour | 95 | 380
| 3 - 400 bbl storage tanks | Crane w/ operator | 8 | Hour | 303.35 | 2426.8
| 1 - 2500 gal reactor tank | Transport/winch | 8 | Hour | 162.46 | 1299.68
| 1 - 55 gallon tank and pump | Roustabout crew | 20 | Hour | 200 | 4000
| Misc piping, stairs, blower and heater | Electrician | 4 | Hour | 105 | 420
1 - 16' x 20' metal building
1 - electric generator
| Subtotal |  |  |  |  | 8526.48
| Contingency 10% |  |  |  |  | 852.648
| Subtotal |  |  |  |  | 9379.128
(1) From: RS Means Heavy Construction Cost Data (2014)
BLM Administration
| Procurement Spec | Procurement Spec | 32 | Hour | 20 | 640
| Engineer | Engineer | 24 | Hour | 33.5 | 804
| Subtotal |  |  |  |  | 1444
| Grand Total |  |  |  |  | 10823.128